## Templete IW37N on PM App
0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
MntPlan | Order | Type | MAT | Bsc start | Act.finish | System status | OpAc | Operation short text | Description | C | Op.WorkCtr | Work | Act. work | Un. | Equipment | Equipment descriptn | Functional Loc. | FunctLocDescrip.
356964 | 4000322210 | ZB02 | 2 | 04.10.2020 |  | CRTD MANC NMAT PRC | 10 | 6M - EE BAG MAKER | PM-Cleaning inside & electrical 4A8 |  | PAC002 | 1080 | 0 | MIN | 10051515 | BAG MAKER 4A8 | PI-TH-7151-FA-PK-04 | PACKING AREA ZONE PK4
356961 | 4000322228 | ZB02 | 2 | 04.10.2020 |  | CRTD MANC NMAT PRC | 10 | 6M - ME BAG MAKER | PM-Time base End seal bag maker 4A8 |  | PAC002 | 2880 | 0 | MIN | 10051515 | BAG MAKER 4A8 | PI-TH-7151-FA-PK-04 | PACKING AREA ZONE PK4
356963 | 4000322229 | ZB02 | 2 | 04.10.2020 |  | CRTD MANC NMAT PRC | 10 | 1M - ME BAG MAKER | PM-Time base strip unit bag maker 4A8 |  | PAC002 | 960 | 0 | MIN | 10051515 | BAG MAKER 4A8 | PI-TH-7151-FA-PK-04 | PACKING AREA ZONE PK4
356960 | 4000322231 | ZB02 | 2 | 04.10.2020 |  | CRTD MANC NMAT PRC | 10 | 6M - ME BAG MAKER | PM-Time base Back seal bag maker 4A8 |  | PAC002 | 2880 | 0 | MIN | 10051515 | BAG MAKER 4A8 | PI-TH-7151-FA-PK-04 | PACKING AREA ZONE PK4
356952 | 4000322236 | ZB02 | 2 | 04.10.2020 |  | CRTD MANC NMAT PRC | 10 | 6M - ME BAG MAKER | PM-Time base Back seal bag maker 4A7 |  | PAC002 | 2880 | 0 | MIN | 10051514 | BAG MAKER 4A7 | PI-TH-7151-FA-PK-04 | PACKING AREA ZONE PK4
356962 | 4000322237 | ZB02 | 2 | 04.10.2020 |  | CRTD MANC NMAT PRC | 10 | 6M - ME BAG MAKER | PM-Time base Film feed bag maker 4A8 |  | PAC002 | 360 | 0 | MIN | 10051515 | BAG MAKER 4A8 | PI-TH-7151-FA-PK-04 | PACKING AREA ZONE PK4
610000004075 | 4000325517 | ZB02 | 2 | 02.10.2020 |  | CRTD MANC NMAT PRC | 10 | 6M- ME Fryer Zone (P15) | 610000004075 & P15-HR-ME |  | PRO001 | 960 | 0 | MIN | 10051386 | Fryer Zone | PI-TH-7151-FA-F1-P1 | FACTORY 1 PC50MZ
356972 | 4000325580 | ZB02 | 2 | 11.10.2020 |  | CRTD MANC NMAT PRC | 10 | 6M - EE BAG MAKER | PM-Cleaning inside & electrical 4A9 |  | PAC002 | 1080 | 0 | MIN | 10051518 | BAG MAKER 4A9 | PI-TH-7151-FA-PK-04 | PACKING AREA ZONE PK4
361488 | 4000326847 | ZB02 | 1 | 04.10.2020 |  | CRTD MANC NMAT PRC | 10 | 1Y - EE Oil Heating Zone (P14) | 361488 & P14-YI-EE |  | PRO002 | 240 | 0 | MIN | 10049361 | Oil Heating Zone | PI-TH-7151-FA-F1-P1 | FACTORY 1 PC50MZ
610000004076 | 4000327140 | ZB02 | 2 | 25.10.2020 |  | CRTD MANC NMAT PRC | 10 | 1Y- ME Fryer Zone (P15) | 610000004076 & P15-YR-ME |  | PRO001 | 960 | 0 | MIN | 10051386 | Fryer Zone | PI-TH-7151-FA-F1-P1 | FACTORY 1 PC50MZ
357294 | 4000327192 | ZB02 | 2 | 02.10.2020 |  | CRTD MANC NMAT PRC | 10 | 6M - ME BAG MAKER | PM-Time base Vacuum pump 5A13 |  | PAC002 | 120 | 0 | MIN | 10055739 | BAG MAKER 5A13 | PI-TH-7151-FA-PK-05 | PACKING AREA ZONE PK5
356933 | 4000327199 | ZB02 | 2 | 17.10.2020 |  | CRTD MANC NMAT PRC | 10 | 6M - ME BAG MAKER | PM-Time base End seal bag maker 4A5 |  | PAC002 | 2880 | 0 | MIN | 10051512 | BAG MAKER 4A5 | PI-TH-7151-FA-PK-04 | PACKING AREA ZONE PK4
357326 | 4000327206 | ZB02 | 2 | 02.10.2020 |  | CRTD MANC NMAT PRC | 10 | 6M - ME BAG MAKER | PM-Time base Vacuum pump 5A14 |  | PAC002 | 120 | 0 | MIN | 10055740 | BAG MAKER 5A14 | PI-TH-7151-FA-PK-05 | PACKING AREA ZONE PK5
357426 | 4000327207 | ZB02 | 2 | 02.10.2020 |  | CRTD MANC NMAT PRC | 10 | 6M - ME BAG MAKER | PM-Time base Vacuum pump 6A9 |  | PAC002 | 120 | 0 | MIN | 10051308 | BAG MAKER 6A9 | PI-TH-7151-FA-PK-06 | PACKING AREA ZONE PK6
357444 | 4000327208 | ZB02 | 2 | 02.10.2020 |  | CRTD MANC NMAT PRC | 10 | 6M - ME BAG MAKER | PM-Time base Vacuum pump 6A12 |  | PAC002 | 120 | 0 | MIN | 10051311 | BAG MAKER 6A12 | PI-TH-7151-FA-PK-06 | PACKING AREA ZONE PK6
356941 | 4000327215 | ZB02 | 2 | 17.10.2020 |  | CRTD MANC NMAT PRC | 10 | 6M - ME BAG MAKER | PM-Time base End seal bag maker 4A6 |  | PAC002 | 2880 | 0 | MIN | 10051513 | BAG MAKER 4A6 | PI-TH-7151-FA-PK-04 | PACKING AREA ZONE PK4
610000004067 | 4000328641 | ZB02 | 2 | 10.10.2020 |  | CRTD MANC NMAT PRC | 10 | 6M - ME Oil Heating Zone (P14) | 610000004067 & P14-HL-ME |  | PRO001 | 120 | 0 | MIN | 10049361 | Oil Heating Zone | PI-TH-7151-FA-F1-P1 | FACTORY 1 PC50MZ
356788 | 4000328659 | ZB02 | 7 | 11.10.2020 |  | CRTD MANC NMAT PRC | 10 | 1Y - EE Flavoring Zone (P17) | 356788 & P17-YC-EE13 |  | PRO002 | 240 | 0 | MIN | 10049372 | Flavoring Zone | PI-TH-7151-FA-F1-P1 | FACTORY 1 PC50MZ
356892 | 4000328682 | ZB02 | 1 | 11.10.2020 |  | CRTD MANC NMAT PRC | 10 | 3M - ME BAG MAKER | 356892 & PK2-QI-ME BAG MAKER |  | PAC002 | 60 | 0 | MIN | 10051716 | BAG MAKER 2A12 | PI-TH-7151-FA-PK-02 | PACKING AREA ZONE PK2
610000004131 | 4000330152 | ZB02 | 1 | 02.10.2020 |  | CRTD MANC NMAT PRC | 10 | 2M - EE Oil Heating Zone (P14) | 610000004131 & P14-NI-EE3 |  | PRO002 | 60 | 0 | MIN | 10049361 | Oil Heating Zone | PI-TH-7151-FA-F1-P1 | FACTORY 1 PC50MZ
351959 | 4000330360 | ZB02 | 18 | 12.10.2020 |  | CRTD MANC NMAT PRC | 10 | 1Y - EE Oil Heating Zone (FR3) | 351959 & FR3-YI-EE |  | PRO002 | 60 | 0 | MIN | 10049451 | Oil Heating | PI-TH-7151-FA-F1-FP | FACTORY 1 FRYPACK
351909 | 4000330361 | ZB02 | 18 | 12.10.2020 |  | CRTD MANC NMAT PRC | 10 | 1Y - EE Boiler & Hot Water Zone (PE7) | 351909 & PE7-YI-EE |  | PRO002 | 240 | 0 | MIN | 10049436 | Boiler/Hot Water | PI-TH-7151-FA-F2-PL | FACTORY 2 Pellet
351958 | 4000330363 | ZB02 | 18 | 12.10.2020 |  | CRTD MANC NMAT PRC | 10 | 1Y - EE Oil Heating Zone (ST5) | 351958 & ST5-YI-EE |  | PRO002 | 60 | 0 | MIN | 10051747 | Oil Heating | PI-TH-7151-FA-F1-ST | FACTORY 1 STAX
356822 | 4000330374 | ZB02 | 1 | 06.10.2020 |  | CRTD MANC NMAT PRC | 10 | 6M - EE Flavoring Zone (P17) | 356822 & P17-HI-EE12 |  | PRO002 | 60 | 0 | MIN | 10049372 | Flavoring Zone | PI-TH-7151-FA-F1-P1 | FACTORY 1 PC50MZ
351910 | 4000330379 | ZB02 | 18 | 12.10.2020 |  | CRTD MANC NMAT PRC | 10 | 1Y - EE Oil Heating Zone (P14) | 351910 & P14-YI-EE |  | PRO002 | 120 | 0 | MIN | 10049361 | Oil Heating Zone | PI-TH-7151-FA-F1-P1 | FACTORY 1 PC50MZ
361276 | 4000330400 | ZB02 | 33 | 06.10.2020 |  | CRTD MANC NMAT PRC | 10 | 2W - ME Cutting & Embrossing Zone (SX3) | 361276 & SX3-FL-ME2 |  | PRO001 | 15 | 0 | MIN | 10049663 | Cutting & Embrossing | PI-TH-7151-FA-F1-SC | FACTORY 1 SCHAAF 2
| 4000330650 | ZB05 | 3 | 07.10.2020 |  | REL NMAT PRC SETC | 10 | modification multipack STAX | modification multipack STAX |  | PAC010 | 0 | 0 | H | 10050867 | STAX BUNDLE SB-001 | PI-TH-7151-FA-PK-ST | PACKING AREA STAX ZONE
| 4000331011 | ZB05 | 3 | 08.10.2020 |  | REL NMAT PRC SETC | 10 | สั่งซื้อ Contact heater endseal | สั่งซื้อ Contact heater endseal |  | PAC000 | 0 | 0 | H | 10051714 | BAG MAKER 5A6 | PI-TH-7151-FA-PK-05 | PACKING AREA ZONE PK5
| 4000331012 | ZB05 | 3 | 08.10.2020 |  | REL NMAT PRC SETC | 10 | สั่งทดลองทำเฟือง Drive back seal | สั่งทดลองทำเฟือง Drive back seal |  | PAC000 | 0 | 0 | H | 10070565 | BAG MAKER 4A1 | PI-TH-7151-FA-PK-04 | PACKING AREA ZONE PK4